## About
Contract Management Capability Programme
Contract Tiering Guide
The purpose of contract tiering
With central government departments and the wider public sector organisations now buying increasingly complex goods and services, there is a need to mitigate risk of failure, improve contract efficiency and demonstrate greater efficiency by having confident individuals in place to manage these elements.
Effective tiering, using various measures to cover factors such as the potential impact of service failure, the speed and ease of switching suppliers, and contract value helps to categorise contracts into GOLD (most critical), SILVER and BRONZE (least critical) for the purposes of assessing risk and mitigating failure.
About this guide
Contract tiering is not a ‘tick box’ exercise. There are factors which must come into play before deciding upon how a contract is classified. Tiering should form a part of the overall process by which a contract is managed after it has been signed. Classification should be used to determine the level of risk presented by a contract, and therefore the level of contract management and level of skills which will need to be applied.
This guide has been developed in collaboration with a working group drawn from Contract Management Capability Programme leads and accredited specialists.
Identify contracts (value, complexity, risk,social value)
Bronze | Silver | Gold
Levels of training and accreditation
Foundation | Practitioner | Expert
Version Control
Version: 3.0 (Version 2.0 was 2024) | Owner: andrew.knight@cabinetoffice.gov.uk - SRO Contract Management Capability Programme
Date: Sep 2025 | Authors: tom.barlow@cabinetoffice.gov.uk and richard.waft@cabinetoffice.gov.uk
Sustainability

## Guidance
Contract Management Capability Programme
Tiering Tool Guidance
General guidance
• | This tiering tool is a living document designed to be used over the lifetime of a requirement - to determine the level of risk presented by a procurement, and the resulting contract.
• | Where possible the tool should be completed by both the procurement team and contract management team
• | This tool should be based upon information available at the time. This will determine the contract management requirement, the resources and any training that should be put in place
• | Using the tool as early as possible in the process will help with the overall pipeline and capacity / resource planning
• | This tiering tool should be revisited following contract award to update the level of risk presented, resources and training required
• | The tiering tool should be used for every contract and each version saved along with any other documentation for the contract
• | The information and any override approval should be recorded in the tool (a new version saved each time)
• | It is good practice to record all contract tiers and any overrides (in the contract database system used by the department/organisation) for auditing purposes.
• | Please revisit the tool if there are any contract variations during the life of the contract that will impact value, complexity or risk.
• | Once complete, please use the details in the Final Summary to alert the appropriate teams and drive the right activities (business cases, funding, procurement teams, CM teams, resourcing/recruitment)
Completing the tool
• | You only need to provide specific information in the Tool Input and Manual Override tabs.
• | In most cases you will only need to complete the Red boxes on the Tool Input sheet and if applicable on the Manual Override sheet.
• | Please enter all of the contract information at the top of the input page - as this helps drive the required tier and accreditation in some cases.
• | The tool should be completed by selecting an option from the drop-down menu in column E, for each of the metrics in column C. Evidence should then be provided in column H to support the selection.
• | Full definitions for each of the levels that can be selected are provided in the Definitions tab and can be used to help decide on the appropriate option.
Manual Override
• | Consideration has been given to updating the tool to allow users to select an alternative prioritisation and weighting, however this only really impacts contracts that are borderline Bronze/Silver and Silver/Gold.
• | Having just one consistent tool allows borderline contracts to be moved/tiered using the override process
• | Any decision to alter a classification must be made by a senior manager (procurement lead/SRO etc.). This must be documented using the manual override sheet.
• | You should stick with the tier that the tool suggests unless the contract does not sit well with the level descriptions and ends up with a borderline outcome.
• | If a contract is clearly bronze, silver or gold, then it should remain that way.
Using the output
• | The Final Summary shows all of the information from the initial input and any subsequent override.
• | The tiering of the contract should drive the commercial and operational decisions required ahead of procurement and subsequent 'go live'.
• | The tiering should drive the level of contract management that is required and time that should be allocated to this.
• | The tiering shows the accreditations that should be in place in order to manage the contract effectively and with the required assurances.
• | Where accreditations are not in place early use of the tool will enable training to start at the earliest opportunity - and for the appropriate mitigations to be put in place.
• | The contract tier, contract manager and any mitigations should be recorded for audit / assurance purposes.
What if the tool does not quite work for you?
• | The preferred option is to tier as the tool describes and assign the correct level of contract management to the contract
• | If this is not possible (for example, where an organisation has a large number of high value contracts and an independent view of risk), then:
i. Tier as normal but record separately the level of contract management provided to the contract, and record the use of a practitioner as a practical step to CM
ii. Tier as planned (for continuity) and use the override function with an explanation
iii. Change the tier values in question 1.1 by changing the levels in the hidden vlookuptables tab

## Tool Input
Contract Management Capability Programme
Tiering Tool Input Sheet
Purpose
Users are to provide headline contract data and select the appropriate response to each question in order to tier the contract.
Guidance
Please fill in the contract information below
To classify your contract, please select the most appropriate option from the drop down list for each of the questions listed
Please see the 'Definitions' tab for more details on the descriptions
Please provide any reasoning/justification in the evidence column
Contract Information
Contracting authority | TBC | Contracting authority an OGD? | TBC | Contract dates |  | TBC
Supplier | TBC | Contract on the GMCP? | TBC | Tool completed by |  | TBC
Contract name | TBC | Is there an SRO? | TBC | Date of completion |  | TBC
Contract reference / OCID | TBC | Is this contract a PFI? | TBC | Tool input reviewed by |  | TBC
Main procurement category | TBC | Date signed | TBC | Date of review |  | TBC
Value
1.1 What is the Total Contract Value or expected Total Contract Value (incl. possible extensions)?
Complexity |  | Select | Description |  | Evidence
2.1 How complex is the delivery or expected delivery of the goods/services? |  |  |  |  | TBC
2.2 How quickly could organisation switch suppliers or reprocure the contract? |  |  |  |  | TBC
Risk Analysis |  | Select | Description |  | Evidence
3.1 What is the potential impact of contract/supplier failure? |  |  |  |  | TBC
3.2 Information Security Risk |  |  |  |  | TBC
Sustainability | More info here | Select | Description |  | Evidence
4.1 How relevant is sustainability (taking into account risks, issues, opportunities) to your requirement? |  |  |  |  | TBC

## Manual Override
Contract Management Capability Programme
Manual Override
Purpose
This sheet allows the contracting organisation to alter the tiering of the contract, understand the implications and formally record the change
Guidance
The tiering from the tool should only be overridden where the descriptions/levels do not quite work for the contract in question
The tier should only be overridden in situations where the outcome is borderline Bronze/Silver or Silver/Gold
The tier should not be overridden to enable the contract manager's level of accreditation to suit the contract
Check for any conflicts and reconsider the override if necessary
Use the Manual Override box to override the tier
Manual override
Is a manual override required |  |  | No
Contract value override
If the rationale for changing the tier is solely down to contract value, whereby the values given by cabinet office do not reflect the organisations internal rules, then please input your own values below. Then re answer question 1.1 on the right hand side
Is the rationale for changing the tier is solely down to contract value? |  |  | No | Proceed to the below manual override area
Risk | Bottom of band (m) | Top of band (m)
Very High | 20 | & Over | 1.1 What is the Total Contract Value or expected Total Contract Value (incl. possible extensions)?
High | 5 | 20
Medium | 1 | 5
Low | Less Than | 1
Tier based on Cabinet Office values |  | 0 / 90
New tier based on value adjustment |  | 0 / 90
Does this change result in any conflicts |  | No
No
Manual override
If the rationale for changing the tier is down to other factors and not value, then please complete this section
Rationale for changing the tier of the contract
Tier based on Cabinet Office values |  | 0 / 90
Manual override tier |  |  | No Override
Does this change result in any conflicts |  | No
No

## Output Summary
Contract Management Capability Programme
Output Summary
Purpose
This tab shows the output from the Tiering Tool and if there has been any overrides. It also explains the training/accreditation required and recommended
Guidance
Output only. Check for conflicts and correct in the input tool if necessary
Contract Information
Contracting authority | TBC | Contracting authority an OGD? | TBC | Contract dates |  | TBC
Supplier | TBC | Contract on the GMCP? | TBC | Tool completed by |  | TBC
Contract name | TBC | Is there an SRO? | TBC | Date of completion |  | TBC
Contract reference / OCID | TBC | Is this contract a PFI? | TBC | Tool input reviewed by |  | TBC
Main procurement category | TBC | Date signed | TBC | Date of review |  | TBC
Output from tool
Area | Level |  | Reasoning
Value | 0
Complexity | 0 |  | TBC
Supplier Switch Difficulty | 0 |  | TBC
Failure Impact | 0 |  | TBC
Information Risk | 0 |  | TBC
Social Value | 0 |  | TBC
Score from Tool | 0 / 90
Are there any conflicts
Manually overriden
Reason For Manual Override |  | No Override
0
Training requirements |  | Training Information
Sustainability |  | Please contact the capability team- gcfengagement@cabinetoffice.gov.uk |  |  | More info can be found here
SRO training required | No
PFI training required | No
Additional training recommended | Beyond Foundation
Should your contract be on the GMCP?
The Government Major Contracts Portfolio (GMCP) is an initiative within the Government Commercial Function (GCF). The primary purpose of the GMCP is to enable reporting, progressive assurance, and targeted intervention on the central government's most critical contracts.
Is your contract eligible for review by the team? |  | No
If your contract is eligible for review by the GMCP team, please sumbit a request to - The information to submit is as follows;

## Definitions
Contract Management Capability Programme
Definitions
Purpose
The definitions should be used to help decide the level in accordance with the tool itself. These will help you decide on the right level of value, complexity and risk for the contract.
Guidance
Choose the level that best describes the risk associated with the contract. If uncertain between two levels, choose the higher risk level and review the validity at the end.
Contract Questions
Is the contracting organisation an OGD?
Please select 'Yes' if the contracting organisation is a Central Government Department
Is the contract on the GMCP?
The GMCP is the Government Major Contract Portfolio and comprises the 70-100 largest/highest profile/highest risk contracts Please select 'Yes' if you know the contract is listed on the GMCP, or you suspect it may be on the GMCP radar due to its size/complexity/risk All contracts on the GMCP are classified as Gold and require an Expert-accredited contract manager, and are led by a SRO with SRO training
Does the contract have an SRO?
Large-scale contracts and programmes require a SRO (Senior Responsible Owner) to be in place It is good practice to appoint an SRO All SROs should have SRO Module 1 training, which provides an excellent high-level guide to being an effective SRO (available at the Government Commercial College) SROs for major contracts and programmes may be formally/publicly appointed and would benefit from the in-depth SRO training available
Is the contract a PFI?
Some contracts are funded by a Private Finance Initiative (PFI) These are typically very long term contracts of high value/complexity/risk and should be Gold contracts All PFIs require an Expert-accredited contract manager, who is also PFI trained (the IPA course available at the Government Commercial College) All PFIs should also have an SRO with SRO training
1.1 What is the Total Contract Value or expected Total Contract Value (including possible extensions)?
£10 million and over
Between £2.5m and £9.99 million
Between £250,000 and £2.49 million
Between £0 and £250,000
2.1 How complex is the delivery or expected delivery of the goods/services?
Very Complex - Contracted provision or expected provision includes three or more of the following :
1. Large number of different goods/ services, with different payment and monitoring requirements for each category
2. Complex payment provisions (fixed and variable payments requiring regular verification of invoices/ and issue of multiple / updated POs; regular price changes due to contract variations/ benchmarking)
3. Complex incentive mechanism (combination of deductions/ ratchets/ withholding parts of payment for partial under-performance/ non-provision; incentive payments; profit share)
4. Large volume of contract changes (major regular changes and/or large number of smaller changes)
5. Expected/ existing large volume of disputes and escalations (e.g. in case of provision of high impact goods/ services to large numbers of end users, such as IT support or FM provision)
6. Benchmarking is built into the contract
7. Supplier is expected to deliver continuous innovation / development, which requires regular adjustments to contract/ specification/ scope/ payment regime
8. Two years and above in duration
Sustainability
Complex - Contracted provision or expected provision includes between one and three of the following :
1. Large number of different goods/ services, with different payment and monitoring requirements for each category
2. Complex payment provisions (fixed and variable payments requiring regular verification of invoices/ and issue of multiple / updated POs; regular price changes due to contract variations/ benchmarking)
3. Complex incentive mechanism (combination of deductions/ ratchets/ withholding parts of payment for partial under-performance/ non-provision; incentive payments; profit share)
4. Large volume of contract changes (major regular changes and/or large number of smaller changes)
5. Expected/ existing large volume of disputes and escalations (e.g. in case of provision of high impact goods/ services to large numbers of end users, such as IT support or FM provision)
6. Benchmarking is built into the contract
7. Supplier is expected to deliver continuous innovation / development, which requires regular adjustments to contract/ specification/ scope/ payment regime
8. Two years and above in duration
9. High savings potential
Relatively Straightforward - Contracted provision or expected provision includes one or more of the following :
1. More than one category of goods/ services
2. Combination payment provisions (payments require some adjustment during life of the contract due to variable volumes of provision, which require occasional adjustment to POs/ review of invoices; combination of single type of fixed and variable fees)
3. Basic Incentive mechanism (e.g. fixed level of deductions linked to clear and concise non-performance criteria)
4. Moderate volume of contract changes (e.g. 1 major change and 2-3 small changes per annum)
5. Moderate risk of regular/ major disputes and escalations
6. One or two years duration.
7. Low/medium savings potential.
Straightforward - Contracted provision or expected provision includes one or more of the following:
1. Single category of goods / services
2. One type of payment provisions (fixed rates or fixed cost for duration of contract)
3. Low expected volume of contract changes for duration of contract
4. Low risk of escalation
5. Below one year.
6. Limited savings potential
2.2 How quickly could the organisation switch suppliers or reprocure the contract?
Would take over six months - Limited options, significant effort, resources and time to switch supply with some acknowledged risks:
1. Only one or two credible alternative suppliers
2. High concentration of / reliance on a small number of sub contractors
3. Difficult to set up the service in house
4. Heavily embedded resources / complicated structure that difficult to separate.
5. Information to make changes is difficult to access and understand - to facilitate TUPE etc.
6. There are significant dependencies on the supplier that are not easily mitigated.
Would take between three and six months - Some supply options. Some fffort and resources are required to switch supply with manageable risks:
1. Two or three credible alternative suppliers
2. Some concentration of sub contractors
3. Time required to establish approvals, resources, funding but all possible over time.
4. Embedded resources / complicated structures but possible to separate with planning.
5. Information to make changes is available but complicated and requires planning to facilitate TUPE etc.
6. There is dependency on the supplier which would take significant effort to mitigate.
Would take between two and three months - There are options available and manageable challenges and a supplier switch could be achieved in a timely manner:
1. three to four credible alternative suppliers
2. No or small level of concentration of sub contractors
3. Relatively simple to set up in house with a small number of steps and processes to achieve.
4. Some complication around resources, but possible to identify and separate.
5. Information to make changes is available and changes / movement is possible with some planning.
6. Some limited dependencies on the supplier which can be mitigated.
Under eight weeks, or can be brought in-house - Multiple options available and resources are available to switch supply and can be achieved in a short period of time:
1. Multiple credible alternative suppliers
2. Multiple sub contractors available providing choice and reducing risk
3. Simple to set up in house (funding, resources, approval)
4. Simple, identifiable and stand alone resources that can be easily separated.
5. Information available and simple - to create processes for movement.
6. No long term dependencies - simple supply that can easily be replicated
3.1 What is the potential impact of contract/supplier failure?
High - Contracted provision is, or is expected to be, one or more of:
1. A core function of the client organisation
2. Delivers high visibility service to external end users
3. If interrupted, would represent a potentially significant risk to public health, public safety, national security, administration of justice or collection of tax
4. Is of high political importance
5. Delivered to all/ majority of client organisation's employees and is essential to performance of their duties
Medium - Contracted provision is or is expected to be one or more of:
1. Supports or partly delivers a core function of the client organisation
2. Has impact on external end users
3. Has moderate political impact
4. Delivered to several parts of the client organisation and/or has some impact on their ability to perform their duties
Low - Contracted provision is, or is expected to be, one or more of:
1. Only supports or partly delivers a non-core function, or would have very limited impact on a client organisation's core function
2. Has minimal impact on external end users
3. Has minimal political impact
4. Delivered to several parts of the client organisation but has minimal impact on their ability to perform their duties
Very Low - Contracted provision is, or is expected to be, one or more of:
1. Is not part of and doesn't have impact on client organisation's core function
2. Is not visible to external end users
3. Has no political importance and/or of no interest to general public
4. Is provided to small proportion of the client organisation's employees
3.2 Information security risk?
Critical Severity - Sensitive data, would cause significant distress
1. Most severe security incidents and woud typically cause harm to 'company' or 'customer'
2. Highly sensitive data including medical, financial and/or confidential technical specifications
3. Significant risk to provider, user data and security
4. Long term impacts
5. Significant reputational damage, trust and financial implications
6. Likely impact to goods/services provided
High Severity - Sensitive data, potentially causing distress
1. Could result in incidents involving some sensitive data and could cause significant harm to 'company' or 'customer'
2. The provision of sensitive personal data and/or technical specifications that could cause significant harm.
3. Usually impact spread over short and longer term
4. Some reputational damage and risk to trust
5. Possible impact to goods/service provision
Moderate Severity - Data transferred/collected not sensitive
1. Could result in incidents where the release of limited information and may cause some/limited harm to 'company' or 'customer'
2. Could include names and addresses but no specific information
3. More information shared but nothing that could fundamentally impact the provider, supplier, service or competition
4. Minor impact on provision
Low Severity - No data transferred or collected
1. Could result in minor incidents that do not result in material harm to 'company' or 'customers'
2. Possibly goods contracts without confidential technical specifications
3. Possibly 'impersonal' services (e.g. building services)
4.1 How relevant is sustainability (taking into account risks, issues, opportunities) to your requirement?
High - potential to create significantly disproportionate distress/adverse impacts on people and/or the environment
There are risks or issues which have the potential to create significantly disproportionate distress/adverse impacts on people and/or the environment. There is likely to be a disproportionately high cost (e.g. exceeding total contract value) associated with containing any sustainability-related events, which could be one-off or cumulative, should they occur. Identified actions or industry best practices are likely to be inadequate in addressing the severity of risk/ issues. There are a range of high-impact, innovative and long-term sustainability opportunities which could lead to improvements to people and/or the environment. To realise such opportunities, substantial further expertise and resourcing is required, e.g. to shape requirement design or to support procurement & contract delivery.
Medium - potential to create disproportionate distress/adverse impacts to people and/or environment
There are risks or issues which have the potential to create disproportionate distress/adverse impacts to people and/or environment. There is likely to be high costs (e.g. 50% or more of total contract value) associated with containing sustainability-related events, which could be one-off or cumulative, should they occur. Identified actions or industry best practice will partially mitigate the severity of risk/issues. There are several sustainability opportunities which could lead to improvements to people and/or environment. To better understand opportunities and realise benefits, additional resources are required, e.g. to shape requirement design or to support procurement & contract delivery.
Low - risks / issues that may impact people and/or the environment are of low significance
Although there are risks / issues that may impact people and/or the environment, they are of low significance and can be remedied easily at low cost (e.g., less than 50% of total contract value). Identified actions or industry best practices will largely mitigate the severity of any risks/issues. There are limited sustainability opportunities associated with the good/service which could lead to improvements to people and/or the environment. Some small-scale, ‘easy-to-implement’ initiatives may exist. Additional resources are unlikely to be required.
Very Low - risks/issues are not expected to cause harm or negatively affect people and/or the environment
Identified sustainability risks/issues are not expected to cause harm or negatively affect people and/or the environment. There is high confidence that the goods/services are sustainable. Addressing any issues incurs negligible cost. There are minimal / no evident sustainability opportunities which could lead to improvements to people and/or the environment, and no further resources are required.

## Sustainability
Contract Management Capability Programme
Supporting guidance for sustainability & social value
Purpose
To help with understanding which level of risk applies to your contract
Supporting guidance
Sustainable procurement can be seen as the process of acquiring goods and services in a way that ensures value for money on a lifecycle basis while considering environmental, social, and economic impacts. Commercial teams are encouraged to answer the sustainability tiering question according to their existing knowledge and complete it to the best of their ability. Teams should take reasonable steps to engage with relevant teams or further expertise as required. If the answer is “Don’t Know”, then it is suggested that the question is defaulted to “High Risk” so that tiering can be addressed through established governance procedures and policies within Departments. Where available, users should make use of relevant sustainability impact assessments and standards (such as ISO20400) to assist in defining risks, issues, mitigations and opportunities. Recommended sustainable procurement training can be found on the Government Commercial College (GCC) [TBD] – please see the following sessions: - Sustainable Procurement Masterclass sessions [include link] - Etc. (TBD)
Reflection areas for this question include:
- Whether your organisation regularly procures the good/service, or if it is an infrequent / unique requirement - The duration of risks/issues/opportunities/impacts - If there are any volume aggregation opportunities to address sustainability either more strategically or at a category level (i.e. do not consider your project in isolation) - Whether the requirement is likely to be intensive in terms of energy, emissions, water, and natural resources - Whether the requirement is likely to cause adverse impacts on nature, or be reliant on sources vulnerable to climate change impacts (e.g. extreme weather) and/or non-renewable energy sources - The existence of a complex, global, or unstable supply chain - The ability to influence key suppliers and internal colleagues regarding risk/issue mitigation or opportunity maximisation - If the good/service relates to any high-risk categories as identified by the Risk Assessment of Modern Slavery (RAMS) tool / involves any high-risk raw materials
Examples of high risk/issues may include, but not be limited to, factors such as:
- chemical spills - adverse impacts to biodiversity hotspots or degradation of biodiversity - major reliance on high-risk commodities - adverse air/noise/water pollution/emissions - existence of harmful/ forever chemicals - reliance on supply bases disproportionately affected by, or vulnerable to, climate change impacts - long-term commitment to intensive use of fossil fuels - intensive use of natural resources which are not supported by a circular economy approach
Examples of high opportunity may include, but not be limited to, factors such as:
- new design methods which drastically reduce carbon emissions - approaches to use novel materials, design out waste, increase circularity - Increased use of nature based solutions which support biodiversity improvement
Sustainability

## Calculations (hidden)
Contract Management Capability Programme
Calculations
Tool Input Scoring
Priority | Scoring Range | Score | Weighted
3 | (4.5-18) | 0 | 0 |  | Value | 0
2 | (5.625-22.5) | 0 | 0 |  | Complexity | 0
4 | (0-13.5) | 0 | 0 |  | Supplier Switch Difficulty | 1
1 | (6.75-28) | 0 | 0 |  | Failure Impact | 0
5 | (2.25-9) | 0 | 0 |  | Information Risk | 0
6 | (2.25-9) | 0 | 0 |  | Social Value | 0
|  | Total | 0 | 0
Manual Overide Scoring contract value
Priority | Scoring Range | Score | Weighted
3 | (4.5-18) | 0 | 0
2 | (5.625-22.5) | 0 | 0
4 | (0-13.5) | 0 | 0
1 | (6.75-28) | 0 | 0
5 | (2.25-9) | 0 | 0
6 | (2.25-9) | 0 | 0
|  | Total | 0 | 0
Conflicts Calc for Manual override
GMCP | 0 | Silver | 0
PFI | 0 | Bronze | 0
GMCP Score | 0
PFI Score | 0
Conflicts Calc for Value Override
GMCP | 0 | Silver | 0
PFI | 0 | Bronze | 0
GMCP Score | 0
PFI Score | 0
Conflicts Calc for summary
GMCP | 0 | Silver | 0
PFI | 0 | Bronze | 0
GMCP Score | 0
PFI Score | 0
Value
Override
Tool
Master Overide
Master Conflict
Training Calculations
Tool Score
Override | FALSE
Which Override | No Override

## Look Up Tables (hidden)
Contract Management Capability Programme
Look Up Tables
1.1 What is the Total Contract Value or expected Total Contract Value (incl. possible extensions)?
£20 million and over
Between £5m and £19.99m
Between £1m and £4.99m
Between £0 and £999,999
2.1 How complex is the delivery or expected delivery of the goods/services?
Very complex | Very complex and/or difficult; complex payment provisions or incentive mechanisms, benchmarking, continuous innovation.
Complex | Complex; large number of different goods/services with different monitoring requirements, combination of payment mechanisms.
Relatively straightforward | Relatively straightforward; more than one type of goods/services, one type of payment provision.
Straightforward | Simple, straightforward; single category of goods/services with one type of payment provision.
2.2 How quickly could organisation switch suppliers or reprocure the contract?
Would take over 6 months | Limited options, significant effort, resources and time to switch supply with some acknowledged risks
Would take between 3 and 6 months | Some supply options. Effort, resources are required to switch supply with manageable risks
Would take between 2 and 3 months | There are options available and manageable challenges and a supplier switch could be achieved in a timely manner
Under 8 weeks, or can be brought in-house | Multiple options available and resources are available to switch supply and can be achieved in a short period of time
3.1 What is the potential impact of contract/supplier failure?
High | Failure would prevent the organisation from delivering one of its critical public facing services or operating. High media/public interest. Potential judicial enquiry.
Medium | Contract failure would have a debilitating effect on delivering a critical public facing service or operating. Moderate media/public interest. Would cause a loss of confidence.
Low | Failure would make it difficult (complex work around, significant additional resource) to deliver public facing services. Low media/public interest. Not considered a fundamental public service, minimal reputational damage.
Very low | In the event of contract failure there is sufficient resource / options to continue. No real media/public interest. Provision relatively unknown, very little chance of reputational damage.
3.2 Information Security Risk?
Critical Severity | Sensitive data, would cause significant distress - most severve security incidents and typically cause harm to 'company' or 'customer'
High Severity | Sensitive data, potentially causing distress - incidents could cause significant harm to 'company' or 'customer'
Moderate Severity | Data transferred/collected not sensitive - incidents result in limited release of information and may cause some harm to 'company' or 'customer'
Low Severity | No data transferred or collected - minor incidents that do not result in material harm to 'company' or 'customers'
4.1 How relevant is sustainability (taking into account risks, issues, opportunities) to your requirement?
High | The situation involves severe, potentially catastrophic environmental and social risks with disproportionately high remediation costs that exceed current best practices, countered by high-impact sustainability opportunities requiring substantial expert resources for realization.
Medium | This scenario presents significant sustainability risks with the potential for disproportionate harm and high remediation costs (over $50\%$ of contract value), which are only partially mitigated by current practices, while also offering several improvement opportunities that require additional resources to fully realize.
Low | This context describes a situation where risks to people and the environment are of low significance, easily remedied at low cost (less than $50\%$ of contract value) using existing best practices, and sustainability opportunities are limited to small-scale, easy-to-implement initiatives requiring no additional resources.
Very Low | The goods/services exhibit high confidence in sustainability with negligible risk of harm or negative impact and minimal to no evident opportunities for further environmental or social improvement, requiring no additional resources.
Manual Override 1.1 What is the Total Contract Value or expected Total Contract Value (incl. possible extensions)?
£20 million & over
Between: £5 - £20 million
Between: £1 - £5 million
Less than £1 million
Other drop downs
Yes
No
TBC
No Override
BRONZE
SILVER
GOLD