## Confirmed Programme
Road Number | Traffic Impact | Start Date | End Date | SWTRA Start Time | SWTRA End Time | Time Category | Direction | From Junction | To Junction | Location
A4232 | Road Closure | 2024-06-03 | 2024-06-04 | 20:00 | 6:00 | Night Time Works | South Bound | A4232 Capel Llanilltern | A4232 Culverhouse Cross | A4232 TOTAL CLOSURE
A4232 | Road Closure | 2024-06-04 | 2024-06-05 | 20:00 | 6:00 | Night Time Works | North Bound | A4232 Culverhouse Cross | A4232 Capel Llanilltern | A4232 N/B TOTAL CLOSURE
A4232 | Road Closure | 2024-07-30 | 2024-07-30 | 20:00 | 6:00 | Night Time Works | North Bound | A4232 Culverhouse Cross | A4232 Capel Llanilltern | CulverHouse Cross to Jct 33 M4
A4232 | Road Closure | 2024-07-29 | 2024-07-29 | 20:00 | 6:00 | Night Time Works | South Bound | A4232 St Fagans Junction | A4232 Culverhouse Cross | A4232 Jct 33 to Culverhouse Cross South Bound
A470 | Road Closure | 2024-06-09 | 2024-06-11 | 20:00 | 6:00 | Night Time Works | South Bound | A470 Abercynon Roundabout | A470 Bridge Street Interchange | A470 SB - Abercynon to Bridge Street
A470 | Road Closure | 2024-06-17 | 2024-06-20 | 20:00 | 6:00 | Night Time Works | South Bound | A470 Abercynon Roundabout | A470 Bridge Street Interchange | A470 Abercynon to Bridge Street Pontypridd
A470 | Road Closure | 2024-06-12 | 2024-06-14 | 20:00 | 6:00 | Night Time Works | North Bound | A470 Broadway Interchange | A470 Abercynon Roundabout | A470 NB Broadway to Abercynon
A470 | Road Closure | 2024-06-02 | 2024-06-03 | 20:00 | 6:00 | Night Time Works | North Bound | A470 Coryton Junction | A470 Taffs Well/Tongwynlais | A470 Coryton to Taffs Well
A4054 | Road Closure | 2024-06-09 | 2024-06-09 | 5:00 | 11:00 | Day Time Works | West Bound | A470 Coryton Junction | A470 Coryton Junction | Coryton Roundabout - Link Road from M4 WB Exit slip to A470 NB including lane 2 closure on J32 WB exit slip road
A470 | Road Closure | 2024-06-05 | 2024-06-06 | 20:00 | 6:00 | Night Time Works | South Bound | A470 Nant Garw Interchange | A470 Taffs Well/Tongwynlais | A470 Nantgarw to Taffs Well
A470 | Road Closure | 2024-06-06 | 2024-06-07 | 20:00 | 6:00 | Night Time Works | North Bound | A470 Nant Garw Interchange | A470 Upperboat Interchange | A470 NB - Nantgarw to Upper Boat
A4054 | Road Closure | 2024-06-03 | 2024-06-04 | 20:00 | 6:00 | Night Time Works | South Bound | A470 Taffs Well/Tongwynlais | A470 Coryton Junction | A470 SB Taffs Well to Coryton
A470 | Road Closure | 2024-06-04 | 2024-06-05 | 20:00 | 6:00 | Night Time Works | North Bound | A470 Taffs Well/Tongwynlais | A470 Nant Garw Interchange | A470 NB Taffs Well to Nantgarw
A4054 | Road Closure | 2024-06-19 | 2024-06-20 | 20:00 | 6:00 | Night Time Works | South Bound | A470 Taffs Well/Tongwynlais | A470 Taffs Well/Tongwynlais | A470 Southbound Entry Slip from Tongwynlais
A48M | Road Closure | 2024-07-08 | 2024-07-09 | 20:00 | 6:00 | Night Time Works | West Bound | A48 (M) J29a St Mellons | A48 (M) J29a St Mellons | A48 M West Bound Carriageway Closure
A48M | Road Closure | 2024-07-09 | 2024-07-10 | 20:00 | 6:00 | Night Time Works | East Bound | A48 (M) J29a St Mellons | A48 (M) J29a St Mellons | A48 M East Bound Carriageway Closure
M4 | Road Closure | 2024-07-01 | 2024-07-03 | 20:00 | 6:00 | Night Time Works | West Bound | M4 J24 Coldra | M4 J28 Tredegar Park | M4 Jct 24 - Jct 28 Westbound Road Closure
M4 | Road Closure | 2024-04-01 | 2024-06-30 |  |  |  | West Bound | M4 J26 Malpas | M4 J28 Tredegar Park | M4 J26 Malpas to J28 Tredegar Park (WB)
M4 | Road Closure | 2024-09-12 | 2024-09-13 | 20:00 | 6:00 | Night Time Works | East Bound | M4 J26 Malpas | M4 J25 Caerleon | Brynglas tunnels EB
M4 | Road Closure | 2024-12-12 | 2024-12-13 | 20:00 | 6:00 | Night Time Works | East Bound | M4 J26 Malpas | M4 J25 Caerleon | Brynglas tunnels EB
M4 | Road Closure | 2024-07-03 | 2024-07-05 | 20:00 | 6:00 | Night Time Works | East Bound | M4 J28 Tredegar Park | M4 J24 Coldra | M4 Jct 28 - Jct 24 Road Closure
M4 | Road Closure | 2024-06-05 | 2024-06-06 | 19:30 | 6:00 | Night Time Works | West Bound | M4 J29 Castleton | M4 J30 Cardiff Gate | M4 JCT 29-30 W/B TOTAL CLOSURE
M4 | Road Closure | 2024-07-31 | 2024-08-01 | 20:00 | 6:00 | Night Time Works | West Bound | M4 J29 Castleton | M4 J30 Cardiff Gate | M4 Jct 29 to Jct 30 Westbound
M4 | Road Closure | 2024-06-06 | 2024-06-07 | 19:30 | 6:00 | Night Time Works | East Bound | M4 J30 Cardiff Gate | M4 J29 Castleton | M4 JCT 30-29 E/B TOTAL CLOSURE
M4 | Road Closure | 2024-08-01 | 2024-08-02 | 20:00 | 6:00 | Night Time Works | East Bound | M4 J30 Cardiff Gate | M4 J29 Castleton | M4 Jct 30 Cardiff Gate to Jct 29
M4 | Road Closure | 2024-08-03 | 2024-08-04 | 20:00 | 6:00 | Night Time Works | East Bound | M4 J30 Cardiff Gate | M4 J29 Castleton | M4 Jct 30 Cardiff Gate to Jct 29
M4 | Road Closure | 2024-06-13 | 2024-06-15 | 20:00 | 6:00 | Night Time Works | West Bound | M4 J37 Pyle | M4 J37 Pyle | M4 J37 Westbound Entry Slip Total Closure
M4 | Road Closure | 2024-06-19 | 2024-06-20 | 20:00 | 6:00 | Night Time Works | West Bound | M4 J37 Pyle | M4 J37 Pyle | M4 J37 Westbound Entry Slip Total Closure
M4 | Road Closure | 2024-06-10 | 2024-06-13 | 20:00 | 6:00 | Night Time Works | East Bound | M4 J38 Margam | M4 J38 Margam | M4 J38 Eastbound Total Closure between the Slips with Up & Over

## Planned Details TBC
Indicative (inclusive)
Scheme / Element No. | Road No. | From | To
Ash Dieback Response | Various | September | March
Environment Cat 2.1 Defects - Actions from Hazard Tree Surveys | Various | September | March
Essential Vegetation Management - Clearing visibility to signs and cameras encroachment | Various | August | March
Cross Network Bridge Renewals | Various | August | March
Souths Wales Strategic Road Network - Local Full Fibre Network | M4 | July | December
A470 Navigation to Abercynon Street lighting Design | A470 | August | February
A470 Cilfynydd depression S/B | A470 | July | July
Nature Recovery - Tree Planting for Recovery | M4 | September | December
Nature Recovery - Landscape Restoration Projects - Gateways and Wales Way | M4 | November | March
Green Corridors Initiative - Tree Planting for Recovery | M4 | September | November
Essential Vegetation Management for Safety and Resilience | M4 | September | March
Note:
Works will primarily be undertaken with hard shoulder / lane 1 closures and primarily at night
Dates are indicative of the months the schemes are likely to progress and are subject to change